## Timesheet
Project Timesheet - February |  |  |  | Project Timesheet - March |  |  |  | Project Timesheet - April |  |  |  |  | Project Timesheet - May
[8 empty] | Date | Name | Duration | Task | Success | Date | Name | Duration | Task | Success
2025-02-23 | Everyone | 1 hour | Meeting on project idea | 2025-03-02 | Everyone | 1 hour | Meeting about requirements, target users & discussions prototypes | 2025-04-01 | Fahim | 2 hours | working on the Flask Backend | TRUE | 2025-05-02 | Femke | 2 hours | refining printed blocks, painting them | TRUE
2025-02-23 | Youri | 2 hours | Research project idea + slide creation | 2025-03-02 | Fahim | 1 hour | UI designs suitable for children, with a focus on simplicity and accessibility. | 2025-04-03 | Youri | 5 hours | Implementing backend, database, dot detection, | TRUE | 2025-05-05 | Femke | 2 hours | Many, many issues printing more blocks. Many issues. | TRUE
2025-02-25 | Femke | 1 hour | Investigating potential technologies to use | 2025-03-03 | Youri | 2 hours | Designing Lo-Fi Prototypes | 2025-04-03 | Firas | 6 hours | Enhance Interfaces & make them responsive | TRUE | week of 5/05 | Femke | 3 hours | Doing evaluation with 9 teachers (only recorded time spoken) | TRUE
2025-02-26 | Firas | 1 hour | Designing initial UI sketches proposal | 2025-03-09 | Everyone | N/A | Meeting Skipped. | 2025-04-04 | Firas | 5 hours | Backend developement and create auth apis and relational database schema | TRUE | 2025-05-03 | All | 30 mins | Meeting | TRUE
2025-02-27 | Youri | 1 hour | Investigating target users | 2025-03-11 | Youri | 30 mins | Investigating ideas to improve "next-generation" aspect of tool | 2025-04-04 | All | 3 hours | Meeting | TRUE | 2025-05-06 | Fahim | 4 hours | Integrating the APIs with the backend | FALSE
2025-02-28 | Fahim | 1 hour | Desigining Template for UI | 2025-03-11 | Fahim | 1 hour 30mins | Research for articles and reports on Computer Vision integration for detecting base-10 blocks | 2025-04-05 | Firas | 5 hours | Backend Integration with the existing frontend | TRUE | 2025-05-06 | Firas | 1h | investigating external camera integration and live video streaming for server-side processing. | TRUE
|  |  |  | 2025-03-11 | Firas | 3 hours | Setting up Flutter app + interfaces development | 2025-04-06 | Firas | 6 hours | Updated UI with new figma design | TRUE | 2025-05-07 | Fahim | 5 hours | Integrating the rest of the APIs with the backend | FALSE
|  |  |  | 2025-03-14 | Everyone | 30 mins | Meeting distributing tasks for progress presentation | 2025-04-06 | Youri | 3 hours | Improving dot detection & real-time stability | FALSE | 2025-05-07 | All | 30 mins | Meeting | TRUE
|  |  |  | 2025-03-14 | Youri | 40 mins | GANTT chart creation | 2025-04-07 | Youri | 2 hours 30mins | Implement backend image processing (not real-time anymore) | TRUE | 2025-05-07 | Youri | 1h 30 mins | Attempting client-side image processing | FALSE
|  |  |  | 2025-03-15 | Youri | 1 hour 30mins | Designing Mid-Fi Prototypes | 2025-04-08 | Fahim | 1 hour 30 mins | Searched on the APIs required | TRUE | 2025-05-07 | Fahim | 2 hours | Replaced old email + password login with name and code | TRUE
|  |  |  | 2025-04-15 | Firas | 2 hours 30 minutes | Research about : Tactile Learning, Competition, and Gamification in Early Childhood Education | 2025-04-11 | Fahim | 2 hours | Made some of the APIs | TRUE | 2025-05-09 | Firas | 4h | Merged Fahim's code, resolved conflicts, and implemented missing logic | TRUE
|  |  |  | 2025-03-16 | Femke | 4 hours 30 minutes | Further researchf or academic sources + writing Requirements Analysis Report | 2025-04-15 | Fahim + Firas | 6 hours | Worked on the Backend | TRUE | 2025-05-09 | Youri | 5h | Implementing UVCCamera for USB camera support. | FALSE
|  |  |  | 2025-03-16 | Everyone | N/A | Meeting Skipped. | 2025-04-16 | Firas | 4 hours | finishing backend + api documentation | TRUE | 2025-05-09 | Youri | 2h 30 mins | Implement phone video streaming & preview visibility on tablet & server communication | TRUE
|  |  |  | 2025-03-16 | Youri | 40 mins | Slides made | 2025-04-18 | All - Fahim | 30 mins | Meeting | TRUE | 2025-05-10 | Youri | 3h | Test setup on blocks, refine CV, refine UI, cleaning codebase | TRUE
|  |  |  | 2025-03-22 | Youri | 1 hour | Implemented camera feed | 2025-04-18 | Youri | 1 hour 30 mins | Improved dot detection with dynamic image resolutions | TRUE | 2025-05-10 | Youri | 2h 30 mins | Writing technical text & making diagram for report | TRUE
|  |  |  | 2025-03-23 | Femke & Youri | 20 mins | Meeting discussing next steps in sprint & task distribution | 2025-04-24 | Youri | 1 hour 10 mins | Merging code & solving issues | TRUE | 2025-05-11 | Youri | 2h | Added logic for reloading the stream + UI elements | TRUE
|  |  |  | 2025-03-23 | Youri | 2 hours | Trying to set up object recognition in Flutter | 2025-04-25 | Youri | 3 hours | Updating Exercise page UI & functionality | TRUE | 2025-05-11 | All - Femke | 30 mins | Meeting | TRUE
|  |  |  | 2025-04-23 | Firas | 1 hour | Investigating ArUco Markers for Real-Time Verification of Base-Ten Block Arrangements | 2025-04-26 | All - Firas | 30 mins | Meeting | TRUE | 2025-05-11 | Youri | 15 mins | Remove star logic in the UI, exercises solve correctly again & fixed navbar for teachers & students | TRUE
[12 empty] | FALSE | week of 12/05 | Femke | 2 hours 30 minutes | Doing evaluation with 8 teachers (only recorded time spoken) | TRUE
|  |  |  | 2025-04-23 | Fahim | 3 hours | Comparing YOLOv8, OpenCV ArUco, and other models to determine the most suitable approach for real-time block detection. | 2025-04-27 | All | 30 mins | Meeting | TRUE | 2025-05-16 | All | 30 mins | Meeting | TRUE
|  |  |  | 2025-04-24 | Firas | 2 hours | Investigating the feasibility of integrating Computer Vision with Flutter | 2025-04-27 | Youri | 5 hours | Merging code & solving issues & making the app demo ready | TRUE | 2025-05-17 | Youri | 40 mins | Annotate code | TRUE
|  |  |  | 2025-03-25 | Youri | 2 hours | Setting up React Native app & camera | 2025-04-27 | Youri | 1 hour | Making diagram & slides (except demo) | TRUE | 2025-05-17 | Firas | 3 hours | Removed the generic sign-up button, enabled teachers to create student profiles, added student progress tracking, and polished the overall UX. | TRUE
|  |  |  | 2025-03-25 | Fahim | 3 hours | Setting up and configuring OpenCV for real-time image capture and processing of block detection. | 2025-04-27 | Firas | 2 hours | Running code and recording demo for presentation | TRUE | 2025-05-17 | Femke | 2 hours 30 minutes | Removed the generic sign-up button, enabled teachers to create student profiles, added student progress tracking, and polished the overall UX. | TRUE
|  |  |  | 2025-03-28 | Youri | Too many hours | Solving Kotlin issues for all computer vision libraries by Mrousavy. | 2025-04-28 | Femke | 1 hour 30 mins | Initial printing of blocks (I had to learn how) | TRUE | 2025-05-19 | All | 30 mins | Meeting | FALSE
|  |  |  | 2025-03-30 | Youri | 5 hours | Making Mid-Fi screens into non-responsive scaffold app in React Native | Week of 28/04 | Femke | 2 hours 30 minutes | Doing evaluation with 7 teachers (only recorded time spoken) | TRUE | 2025-05-19 | Firas | 20 mins | Fixed the issue that was preventing exercises from being solved. | TRUE
|  |  |  | 2025-03-31 | Youri | 6 hours | Redesigning Mid-Fi / Initial attempt at high fidelity based on peer feedback | [5 empty] | 2025-05-19 | Youri | 30 mins | Testing final code, making demo & making slides | TRUE
[13 empty] | 2025-05-22 | All | 20 mins | Final Meeting | TRUE
[13 empty] | 2025-05-22 | Femke | 1h | Making slides, learning presentation, working on report | TRUE
[13 empty] | 2025-05-21 | Femke | 3 hours | Writing report | TRUE
[13 empty] | 2025-05-25 | Femke | 4h 30 min | Writing report | TRUE

## Blad2
Project Timesheet - March
2025-03-02 | Everyone | 1 hour | Meeting about requirements, target users & discussions prototypes
2025-03-03 | Youri | 2 hours | Designing Lo-Fi Prototypes
2025-03-09 | Everyone | N/A | Meeting Skipped.
2025-03-11 | Youri | 30 mins | Investigating ideas to improve "next-generation" aspect of tool
2025-03-14 | Everyone | 30 mins | Meeting distributing tasks for progress presentation
2025-03-14 | Youri | 40 mins | GANTT chart creation
2025-03-15 | Youri | 1 hour 30mins | Designing Mid-Fi Prototypes
2025-03-16 | Femke | 4 hours 30 minutes | Further researchf or academic sources + writing Requirements Analysis Report
2025-03-16 | Everyone | N/A | Meeting Skipped.
2025-03-16 | Youri | 40 mins | Slides made
2025-03-22 | Youri | 1 hour | Implemented camera feed
2025-03-23 | Femke & Youri | 20 mins | Meeting discussing next steps in sprint & task distribution
2025-03-23 | Youri | 2 hours | Trying to set up object recognition in Flutter
2025-03-25 | Youri | 2 hours | Setting up React Native app & camera
2025-03-28 | Youri | Too many hours | Solving Kotlin issues for all computer vision libraries by Mrousavy.
2025-03-30 | Youri | 5 hours | Making Mid-Fi screens into non-responsive scaffold app in React Native
2025-03-31 | Youri | 6 hours | Redesigning Mid-Fi / Initial attempt at high fidelity based on peer feedback

## Blad1
2025-02-23 | Everyone | 1 hour | Meeting on project idea
2025-02-23 | Youri | 2 hours | Research project idea + slide creation
2025-02-24 | Firas | 2 hours | Drafting initial development ideas and project outline
2025-02-25 | Youri | 1,5 hours | Refining the interactive base-ten block idea wrt functionality, UI, requirements & evaluation
2025-02-25 | Femke | 1 hour | Investigating potential technologies to use
2025-02-26 | Firas | 1 hour | Designing initial UI sketches proposal
2025-02-27 | Youri | 1 hour | Investigating target users

## Blad3
Project Timesheet - March
2025-03-02 | Everyone | 1 hour | Meeting about requirements, target users & discussions prototypes
2025-03-02 | Fahim | 1 hour | UI designs suitable for children, with a focus on simplicity and accessibility.
2025-03-03 | Youri | 2 hours | Designing Lo-Fi Prototypes
2025-03-09 | Everyone | N/A | Meeting Skipped.
2025-03-11 | Youri | 30 mins | Investigating ideas to improve "next-generation" aspect of tool
2025-03-11 | Fahim | 1 hour 30mins | Research for articles and reports on Computer Vision integration for detecting base-10 blocks
2025-03-11 | Firas | 3 hours | Setting up Flutter app + interfaces development
2025-03-14 | Everyone | 30 mins | Meeting distributing tasks for progress presentation
2025-03-14 | Youri | 40 mins | GANTT chart creation
2025-03-15 | Youri | 1 hour 30mins | Designing Mid-Fi Prototypes
2025-04-15 | Firas | 2 hours 30 minutes | Research about : Tactile Learning, Competition, and Gamification in Early Childhood Education
2025-03-16 | Femke | 4 hours 30 minutes | Further researchf or academic sources + writing Requirements Analysis Report
2025-03-16 | Everyone | N/A | Meeting Skipped.
2025-03-16 | Youri | 40 mins | Slides made
2025-03-22 | Youri | 1 hour | Implemented camera feed
2025-03-23 | Femke & Youri | 20 mins | Meeting discussing next steps in sprint & task distribution
2025-03-23 | Youri | 2 hours | Trying to set up object recognition in Flutter
2025-04-23 | Firas | 1 hour | Investigating ArUco Markers for Real-Time Verification of Base-Ten Block Arrangements
2025-04-23 | Fahim | 3 hours | Comparing YOLOv8, OpenCV ArUco, and other models to determine the most suitable approach for real-time block detection.
2025-04-24 | Firas | 2 hours | Investigating the feasibility of integrating Computer Vision with Flutter
2025-03-25 | Youri | 2 hours | Setting up React Native app & camera
2025-03-25 | Fahim | 3 hours | Setting up and configuring OpenCV for real-time image capture and processing of block detection.
2025-03-28 | Youri | Too many hours | Solving Kotlin issues for all computer vision libraries by Mrousavy.
2025-03-30 | Youri | 5 hours | Making Mid-Fi screens into non-responsive scaffold app in React Native
2025-03-31 | Youri | 6 hours | Redesigning Mid-Fi / Initial attempt at high fidelity based on peer feedback

## Blad4
Project Timesheet - April
Date | Name | Duration | Task | Success
2025-04-01 | Fahim | 2 hours | working on the Flask Backend | TRUE
2025-04-03 | Youri | 5 hours | Implementing backend, database, dot detection, | TRUE
2025-04-03 | Firas | 6 hours | Enhance Interfaces & make them responsive | TRUE
2025-04-04 | Firas | 5 hours | Backend developement and create auth apis and relational database schema | TRUE
2025-04-04 | All | 3 hours | Meeting | TRUE
2025-04-05 | Firas | 5 hours | Backend Integration with the existing frontend | TRUE
2025-04-06 | Firas | 6 hours | Updated UI with new figma design | TRUE
2025-04-06 | Youri | 3 hours | Improving dot detection & real-time stability | FALSE
2025-04-07 | Youri | 2 hours 30mins | Implement backend image processing (not real-time anymore) | TRUE
2025-04-08 | Fahim | 1 hour 30 mins | Searched on the APIs required | TRUE
2025-04-11 | Fahim | 2 hours | Made some of the APIs | TRUE
2025-04-15 | Fahim + Firas | 6 hours | Worked on the Backend | TRUE
2025-04-16 | Firas | 4 hours | finishing backend + api documentation | TRUE
2025-04-18 | All - Fahim | 30 mins | Meeting | TRUE
2025-04-18 | Youri | 1 hour 30 mins | Improved dot detection with dynamic image resolutions | TRUE
2025-04-24 | Youri | 1 hour 10 mins | Merging code & solving issues | TRUE
2025-04-25 | Youri | 3 hours | Updating Exercise page UI & functionality | TRUE
2025-04-26 | All - Firas | 30 mins | Meeting | TRUE
2025-04-27 | All | 30 mins | Meeting | TRUE
2025-04-27 | Youri | 5 hours | Merging code & solving issues & making the app demo ready | TRUE
2025-04-27 | Youri | 1 hour | Making diagram & slides (except demo) | TRUE
2025-04-27 | Firas | 2 hours | Running code and recording demo for presentation | TRUE